## Introduction
Introduction to “CMMC Level 1 in a Box”
CMMC Level 1 in a Box was created to help small companies develop a cybersecurity compliance program for CMMC Level 1 on their own, without having to pay for consulting services. However, implementing a cybersecurity compliance program – even for CMMC Level 1 – requires some IT knowledge. If your company outsources its IT services, you need to work with that company to develop your cybersecurity program.
CMMC Level 1 in a Box can also be used by any company wanting to develop a cybersecurity program for any level of compliance – the tool makes it easy to get started.
Contents of CMMC Level 1 in a Box
CMMC Level 1 Presentation – the presentation will introduce you to each of the CMMC Domains and associated practices.
CMMC Level 1 Guide – an Excel workbook that can be used to manage the development of your cybersecurity program and guide you through the necessary tasks.
  Getting buy-in from ownership/management and employees
  Network diagram
  IT Asset Inventory
  Data flow
  Continuous improvement
  Documentation
  Risk assessment
  Scope
  Gap analysis
The Guide also provides a template to help attain and maintain compliance.
Data Security Policy Template – CMMC Level 1 does not require that you develop a data security policy, but it is highly recommended, and the template is a tool you can use to develop your policy.
Click on the "Where to Start" tab to begin your cybersecurity compliance program!
Note: A red triangle in the upper right corner of a cell indicates a comment that provides additional information.

## Where to Start
TASK | Status
Assemptions for use of this guide: 1) You have reviewed the cybernc.us website - https://www.cybernc.us/ - so you have a basic understanding of CMMC; 2) you have determined which type of data your company "touches" - FCI or CUI. Note: Documentation is critical for developing a quality management system of any type, including a cybersecurity system. The documentation will become audit artifacts to be used in an audit/assessment. You can keep the majority of your audit artifacts in this workbook to make the information easy well-organized and easy to find.
1. Click on this link to view the CMMC Level 1 Presentation: https://www.cybernc.us/wp-content/uploads/2020/06/CMMC-Level-1-5.28.20.pdf
2. Develop a value proposition for ownership/upper management to get their buy-in. You can use the resources on cybernc.us
3. Introduce employees to the compliance project. They need to understand that the company's culture will be changing, what will be expected of them, the timeline, etc. If they don't feel that they are a part of the change process, it will be difficult to get buy-in. Can use the resources on cybernc.us to assist with introductory training.
4. Draw a network diagram. A network diagram is not required for CMMC Level 1, but is highly recommended.
5. Perform an IT asset inventory. While this is not required for CMMC Level 1, it is impossible to secure your system if you don’t control the assets.
6. Draw a data-flow diagram. It doesn't have to be formal - just need to see how FCI enters your system, is stored/processed/created and how the data leaves your system.
7. Perform a cybersecurity risk analysis
8. Do a "scoping" exercise to narrow the scope of the audit, reduce the risk of data being compromised and reduce the overall cost to your company.
9. Perform a gap analysis
10. Go through each domain tab and write processes and procedures for each practice. Can use the Policy/Procedure template downloaded with this guide.
11. Develop a System Security Plan (SSP)

## Meetings-Training Docs
It is a good idea to record information about all the cybersecurity meetings/training sessions your organization has.
Information to record:
  - Meeting/training subject
  - Date
  - Attendees names
  - Action items with name of responsible person and date the action is due
  - Follow-up on previous action items
You can use this text box to record your meetings/trainings.

## Buy-In
Must have top management buy-in and support – tone at the top is critical to the success of the project. The person/organization tasked with compliance must have the support from "the top" and be given the resources and authority to do the project.
Employees must be informed and given the opportunity to contribute and participate in the process.
Employees need to understand high-level cybersecurity regulation requirements, understand their responsibilities regarding cybersecurity, including reporting incidents and providing suggestions.
The majority of cyberattacks target people; e.g., business email compromise [impersonating trusted people] and email account compromise [compromise a victim’s email account and send convincing emails using their credentials]
Employees are your first line of defense against those attacks, so you need their buy-in that the company culture surrounding cybersecurity is changing
Can use NIST framework to explain the project - (Home security analogy from CyberChat #1)
See CyberChat #1 for additional information - https://www.cybernc.us/2021/01/13/cyberchat-workshop-1/

## Network Diagram
Draw a network diagram showing how IT assets connect. Dotted lines indicate wifi connectivity, solid lines indicate wired connections.
The diagram doesn't have to be formal - it can be drawn free-hand. If you want the diagram to look a little more professional, click on the "Insert" tab above, then click on "Online Pictures". Put equipment in the search field, such as laptop, switch, router, printer, etc. See example. You can do the drawing on this worksheet page to use as an audit artifact.
See CyberChat #2 for additional information: https://www.cybernc.us/2021/01/20/cyberchat-2/

## Asset Inventory
IT Asset | Date Purchased | Make | Model | Version | Serial # | Service Packs | Status (in use, part of inventory, etc.) | Location | Decommission Date | Method of Decommission | Responsible Person/ Department | Add Other Columns as Necessary
Note on A1: User name: Scroll down to line 50 to see a list of example IT assets.
Asset Inventory - Examples of IT Assets
Cloud storage
Contracts with 3rd party technology suppliers
Desktop computers
Digital cameras
Fax machines
Scanners
Keyboards
Laptops
Monitors
Mouse
Printers
Routers
Switches
Servers
Smartphones
Software applications
Software licenses
Tablets
Internet of Things [IoT]
Cables

## Data Flow Diagram
Data Flow Diagram
Diagram the flow of DoD data in your network – from when the data “enters” your network until it flows out of your network. The information may come from the contracting officer, your prime, etc. and may be flowed down to your subs/suppliers.
No need for a formal diagram. The goal is to know how and where the data flows, is stored, transmitted, etc. and who is handling the data and who has access to the data. See example.
This exercise is critical to determining “scope”
Can use this page to diagram data flow using shapes/lines.
See CyberChat #3 for additional information - https://www.cybernc.us/2021/01/27/cyberchat-3-workshop/

## Risk Assessment
RISKS | IMPACT | PROBABILITY
Simple, Informal Cybersecurity Risk Analysis
Cybersecurity risk is defined as risk to organizational operations, resources, and other organizations due to the potential for unauthorized access, use, disclosure, disruption, modification, or destruction of information or IT.
Start by thinking about how secure your company is in general, not just the security of your network. Also, think about the company data that resides on your system – you want to ensure that you’re protecting that data in addition to DoD project data. Identifying your high-risk areas will help determine how you implement CMMC.
Examples of risks below:
Physical Risks – Physical Protection Domain in CMMC
If you have the kind of company where customers, partners and other 3rd parties are in and out all day, your biggest risk might be physical – someone could walk in, sit down at a computer and do damage to your system and data.
Can employees or 3rd parties physically access your office/building after hours? Do you have a way of knowing who is in your office/building after hours?
People Risks – Multiple Domains
For most companies their biggest risk lies with their employees, and typically the risk is high because employees aren’t aware of the cyber risks inherent in their jobs – they click on suspicious links, open suspicious attachments, don’t log out when they leave their workstation, etc. The best way to mitigate this risk is to train your employees regularly.
The other type of “people” risk is associated with the character of your employees. See Personnel Security tab.
Risks will vary for every company.
Record your risks and rate them based on the potential impact to your business and national security, and the probability of it happening - High, Medium or Low; or, if you want more specificity, you can use a model like the one in the figure. Your primary focus in terms of dollars and time should be on High Impact and High Probability areas.
For high-risk areas you may need to consider implementing practices beyond CMMC Level 1.
Additional information can be found in CyberChat #4 - https://www.cybernc.us/2021/02/03/cyberchat-workshop-4/

## Scope
SCOPE
Scope is very important when it comes to being audited, but reducing your scope will also minimize risk and reduce audit and other costs.
Example: You have 50 computer work stations, but only 4 employees work on the DoD contract that contains FCI or CUI. Unless you reduce your scope, you will be audited on your entire information system - including the computer work stations that have nothing to do with the DoD contract.
For additional information, click on this link to access CyberChat #5 - https://www.cybernc.us/2021/02/13/cyberchat-workshop-5/
Ways to reduce scope:
Segment your network - split a network into subnetworks using a combination of firewalls, Virtual Local Area Networks and access controls to prevent employees not associated with the DoD data from accessing it.
Secure enclaves - more thoroughly segmented from the general network environment
In addition to network solutions, employees working on DoD contracts might need to be in a physically different location like a separate office or area.
For additional information about how to scope your network, consider using the Compliance Forge Scoping Guide - https://www.complianceforge.com/free-guides/free-nist-800-171-cybersecurity-compliance-scoping-guide.html

## Gap Analysis
There are a variety of tools available to help you perform a gap analysis. If your company will only be required to meet CMMC Level 1 requirements (no CUI processed, stored, or created), you can use this tool to do your gap analysis. Simply go through each of the domains to determine which of the practices your company is currently performing and which ones are not being performed. Then develop a plan to attain compliance.
If your company will be required to meet CMMC Level 3 requirements, you should consider performing a self-assessment to the DoD Assessment Methodology before working on CMMC Level 3 compliance. The self-assessment will measure your compliance to the 110 controls in NIST SP 800-171.Go to cybernc.us, click on the Blog tab and select the recording for CyberChat workshop #6 for detailed information on tools and resources to help you perform the gap analysis and develop Plans of Action and Milestones (POAMs).
CMMC Level 3 contains the 110 controls in NIST SP 800-171 plus an additional 20 controls/practices. You will need to perform a gap analysis to those 20 practices as well as develop a quality management system framework for your cybersecurity program - robust policies and procedures for each practice.
For additional information on performing a gap analysis, see CyberChat #6 - https://www.cybernc.us/2021/02/17/cyberchat-workshop-6/

## System Security Plan
A System Security Plan (SSP) is not required for CMMC Level 1 compliance; however it is a good idea to develop one. An SSP is required for CMMC Level 3.
Link to SSP template. https://csrc.nist.gov/CSRC/media/Publications/sp/800-171/rev-2/final/documents/CUI-SSP-Template-final.docx
The template can be modified to suit the needs of your company.

## Training
One of the biggest mistakes companies make when attempting to implement a new program is not involving their employees. If you expect your employees to comply with the processes and procedures required for a good cybersecurity program, they need to understand why the program is being implemented and how their role(s) fit into the new program.
You can begin by using the presentations on the cybernc.us website to introduce your employees to the DoD cybersecurity regulations.
Cybersecurity training - like any other training - should be on-going. Training should be scheduled at regular intervals based on your risk profile.
Free cybersecurity training is abundant, so take advantage of training at the following links:
https://www.projectspectrum.io/#!/ - Project Spectrum is an initiative supported by the DoD Office of Small Business Programs and was established to help small businesses with cybersecurity compliance. You will need to set up a free account.
https://www.ies.ncsu.edu/solutions/cybersecurity/ - Cybersecurity information from North Carolina State University Industry Expansion Solutions
https://www.wizer-training.com/ - free training (can be upgraded for a fee). Cybersecurity training presented in layman's terms via short videos.

## Guide for Domains-Controls
There is a tab for each CMMC Domain - including Domains that are not required for CMMC Level 1 certification. It is recommended that you review the information on each tab.
NOTE: Procedures/Forms/Artifacts are NOT required for CMMC Level 1 Certification, but are highly recommended.
Domains are shaded in light green
Below the Domain is the Capability
To the right of the Capability are the Practices - shaded in orange
CMMC Reference column - shows the Practice number
Recommended Action column – a suggestion in understandable language
Current Company Procedure column (gap analysis) – if your company addresses that particular practice, input the process/procedure used. If your process/procedure isn't written down, try to describe what is typically done. If your company does not perform that practice - in other words you are not compliant with that practice, put a plan together to attain compliance (use Plan of Action column). Use the % Complete column to record your progress.
Below are suggested recommendations- they are not required by the standard
  Procedure Notes column – information that should be in your procedure including who, what, when, where and how. Copy information from that cell to the appropriate section of the Data Security Policy Template
  System Security Notes column – additional important information
  Form Needed column – some procedures should include filling out a form. For example, if the company orders a new printer, a form should be filled out prior to ordering to verify the printer’s compatibility with the system and if it is safe to add to the network. New devices of any kind should not connect to the network without approval. The form can be an assessment artifact to prove you are following your procedure. A form can be a simple Word document or writeable pdf
  Template column – shows which practices can use Template 1.
  Training column – while training is not necessarily required for Level 1 certification, it is considered a best practice to train employees/system users on the policies and procedures in place to protect national security, the company network and those using the network. Note: a company's biggest weakness in terms of network security is its people - opening a suspicious attachment, clicking on a suspicious link, etc.
  Assessment (audit) Artifacts column – auditors require proof that a company is doing what they say they are doing. This workbook, the presentation and the Data Security Policy are all audit artifacts. Anything that shows proof is considered an artifact. Artifacts can be procedures, forms, meeting notes/minutes, etc. Note: A written procedure typically becomes an artifact during employee interviews. If employees show they are using the procedure, it will be an artifact.
  Plan of Action - detailed description of how you plan to implement the control
  % Complete - keep track of you progress - 0%, 25%, 50%, 75%, 100%
See CyberChats 7 - 12 for information about each domain and the practices within those domains. - https://www.cybernc.us/category/blog/

## Template 1
Name | Start Date | Organization | Employee ID | New Employee Training Date(s) | Authorized Access to Network | Types of Accounts Authorized | Account Attributes/ Functions/ Restrictions | Strong PW Set Up (per policy) | Hardware/ SW Issued | Date Issued | Model # | Serial # | Physical Access (key, access card) | Access Terminated Date | Exit Interview Date | Date Items Returned (HW/SW/ Access)
John Smith | 43952 | Payroll | 456123 |  | Y | Payroll | Weekdays 8:00 to 5:00 | Y | Laptop | 42005 |  | L485697 | Card 001
[6 empty] | HR | Read only
[6 empty] | Operations | Read only |  | Monitor 1 |  |  | M89324
[6 empty] | Update Social Media |  |  | Monitor 2 |  |  | M32145
[9 empty] | Mouse |  |  | H23156
[9 empty] | Keyboard |  |  | K89972
[9 empty] | Phone |  |  | IC12456
Mary Jones |  | Engineering | 623978 |  | Y | Engineering | Full
[6 empty] | Operations | Read only
Note on H1: User name: Time of day, days of week, location, create/read/update/delete

## Access Control
Domain/Capability | Practice | CMMC Reference | Assessment Guide | Recommended Actions/Description | Current Company Procedure/Process | Procedure Notes - Who, What When, Where and How | System Security Notes | Form/Meeting Notes | Template | Training | Assessment Artifact(s) | Plan of Action | % Complete
ACCESS CONTROL (AC)
Access control is about keeping out unwanted users. Just like you only want authorized people in your home, you only want authorized people/devices to access your data.
C001 - Establish system access requirements | Limit information system access to authorized users and devices | AC.1.001 | - Are authorized users identified? - Template - Are processes acting on behalf of authorized users identified? Ex: software that acts as a user - Are devices (and other systems) authorized to connect to the system identified? Asset inventory - Is system access limited to authorized users, processes and devices? | Every user has a User ID and a complex password/passphrase |  | Identify which department provides the User ID to employees or other users, how the UIDs are provided, as well as guidelines for creating passwords. | Passwords should be complex, should not contains words that can be found in the dictionary, should contain a combination of upper and lower case letters and symbols. No need to change passwords regularly if they are complex and contain enough characters (16) | Consider developing a form that not only provides the user with their UID, but also provides the password complexity requirements - can be part of onboarding for new employees. | Template 1 can be used for multiple practices. You need to name the spreadsheet and reference it in your procedures. | Employees should understand why passwords need to be complex. See graphic below table. | Procedure, Training Record, Template (whatever you decide to name it)
|  |  |  | Users ID and password credential may not be shared |  | Prohibit the sharing of log-on credentials. | Sharing log-on credentials can lead to multiple accounts being compromised. In addition, if the person using someone else's credentials uses the network inappropriately, the owner of the credentials will be held responsible. | N/A |  | Employees/users need to be trained on the importantce of not sharing log-on credentials. | Procedure, Training Record, Template (whatever you decide to name it)
|  |  |  | List those who can use company computers/devices and log onto the network |  | Describe a procedure for determining who can use the company network as well as identify the department responsible for maintaining the information. | The network access log is considered a "record" and should be kept indefinitely. It may need to be used for security incident investigations. | Access form for new users with approval signature(s) | Template 1 |  | Procedure, Training Record, Template (whatever you decide to name it), Meeting Notes - need date/attendees
|  |  |  | Disable username and password when employees leave the company or no longer require access |  | Identify the department(s) responsible for authorizing network accounts to be disabled, the conditions under which network accounts should be disabled and the department responsible for disabling network accounts. | Possible reasons to disable accounts: employees leaves company, employee makes threats to violate network procedures, unacceptible network activity, if account has been compromised. | Account Disable Form with list of conditions. Department responsible can circle/check off which condition(s) apply | Template 1 | All employees/users should be trained so they understand the circumstances around which accounts can be disabled. | Procedure, Training Record, Template (whatever you decide to name it), Meeting Notes - need date/attendees
|  |  |  | New devices that will access the network must be authorized |  | Identify the department(s) that can authorize new devices as well as the department that grants access. | It is critical that unauthorized devices not access the network. Consider developing a method for authorizing device access, such as an approval form that must be signed. | Device Authorization Form with approval signature(s) | Template 1 | Provide training on the risks associated with unauthoized devices accessing the network. | Procedure, Training Record, Device Aproval Forms, Template (whatever you decide to name it)
C002 - Control internal system access | Limit information system access to types of transactions and functions necessary | AC.1.002 | - Are the types of transactions and functions that authorized users are permitted to execute defined? - Is system access limited to the defined types of transactions and functions for authorized users? | Identify authorized users for each type of account |  | Identify the department(s) responsible for determining which users should have rights to the various accounts (e.g. Human Resources, IT, Payroll, Benefits, etc.) and the department responsible for setting up and monitoring access. | Employees/users do not need access to every type of account - they should only have access to the accounts that are necessary for them to do their job. |  | Template 1 | Provide training on the types of accounts employees/users are allowed to access, and that limiting access protects them and the company. | Procedure, Training Record, Template (whatever you decide to name it), Meeting Notes - need date/attendees
|  |  |  | Keep a current list of accounts and users; review and update list regularly |  | Identify which department(s) is responsible for updating, monitoring and reviewing the account user log. Also need procedure for adding/removing users. | As job functions change, so do access requirements, so regular reviews are important. |  | Template 1 |  | Procedure, Review Document w/ dates/times of reviews and result of review - any actions needed
C004 - Limit data access to authorized users and procedures | Verify and control connections to and use of external information systems [external systems are systems you do not control - cloud, internet, customer, sub, supplier, etc.] | AC.1.003 | - Are connections to external systems identified? - Is the use of external systems identified? - Are connections to external systems verified? - Is the use of external systems verified? - Are connections to external systems controlled/limited? - Is the use of external systems controlled/limited? | Employees connect to secured external systems only |  | Procedure that shows how company network only allows connection to secured networks |  |  |  | Train employees on the dangers involved with connecting to unsecured networks and that they should only use company-issued computers/devices to connect to company network | Procedure and training record.
|  |  |  | Limit/control access of 3rd parties such as contractors, visitors, etc. to network |  | Procedure for authorizing 3rd party access and how access will be denied to those who aren't authorized. |  | Form to allow 3rd party access |  |  | Procedure, authorization form, physical access log (who enters the office/building)
|  |  |  | Limit/control access of other systems internal to the company (applies to companies with multiple networks) |  | If you have more than one network, describe the procedure for how users only have access to the network they need to do their work and do not have access to any other network and how unauthorized access is prevented |  |  |  |  | Procedure
| Control information posted on publicly accessible information systems | AC.1.004 | - Are individuals authorized to post or process information on publicly accessible system identified? - Are there written procedures to ensure FCI is not posted or processed on publicly accessible systems? - Is there a review process is in place prior to posting of any content to publicly accessible systems? - Is content on publicly accessible systems is reviewed to ensure that it does not include FCI? - Are mechanisms in place to remove and address improper posting of FCI? | Designate employees who are authorized to post information on public sites - website, Facebook, LinkedIn, Twitter, etc. |  | Identify employees/users who are allowed to post information on social media sites, procedure for how to access the sites, procedure for how others are denied access, and how employees are trained on the types of data they can and cannot post. |  |  | Template 1 | Individuals who are authorized to post information on social media should be thoroughly trained about Federal Contract Information (FCI) | Procedure, Template 1
|  |  |  | Train the designated employees to ensure that publicly accessible information does not contain nonpublic information |  | Procedure for how employees are trained on the types of data they can and cannot post, and how often the training needs to occur. |  |  |  | Develop a training program for employees who are authorized to post on social media sites | Procedure, signed/dated training record
|  |  |  | Review and approve information prior to posting, and review sites frequently |  | Procedure for how the information is reviewed and approved prior to posting, and how often the sites are to be reviewed and by whom |  |  |  |  | Procedure, Signed/dated approval form. Review form (checklist)
Note on D1: User name: Questions assessors/auditors will ask
Note on F1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Write down how your company accomplishes this practice. If you don't do that practice, leave the cell blank
Note on G1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Write a good procedure in this cell using who, what, when, where and how. Copy the procedure into the appropriate section of the Data Security Policy.
Note on M1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What needs to be done to become compliant with the practice in column B
Note on N1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Keep track of your progress - 0%, 25%, 50%, 75%, 100%

## Identification & Authentication
Domain/Capability | Practice | CMMC Reference | Assessment Guide | Recommended Actions/Description | Current Company Procedure/Process | Procedure Notes - Who, What When, Where and How | System Security Notes | Form/Meeting Notes | Template | Training | Assessment Artifact(s) | Plan of Action | % Complete
IDENTIFICATION & AUTHENTICATION (IA)
Identification and Authentication practices ensure the identities of those who have access to data that must be safeguarded. Is the person or device that is logging in who/what they say they are and how will you verify it?
C015 - Grant access to authenticated entities | Identify information system users, procedures acting on behalf of users, or devices. | IA.1.076 | - Are system users identified? Template 1 - Are processes acting on behalf of users identified? - Are devices accessing the system identified? Asset inventory | Assign usernames to all employees/users who access company systems; use those credentials to allow appropriate access |  |  | The objective is to make sure that whoever or whatever (devices) are trying to access your system/accounts/projects are identified and verified - that they are who or what they say they are |  | Template 1 (for devices) | Employees should know that they will be identified and authenticated before access is allowed | Procedure, Template 1 and training record
Identify devices using media access control, IP addresses or device-unique token identifiers prior to allowing access
| Authenticate (or verify) the identity of those users, procedures, or devices, as a prerequisite to allowing access to organizational information systems. | IA.1.077 | - Is the identify of each user authenticated or verified as a prerequisite to system access? - Is the identity of each process acting on behalf of a user authenticated or verified as a prerequisite to system access? - Is the identity of each device accessing or connecting to the system authenticated or verified as a prerequisite to system access | Authenticators include passwords, key cards, one-time password devices, etc. Change default/temporary usernames and passwords. |  |  |  |  | Template 1 for key-cards or other devices | Employees should know that they will be identified and authenticated before access is allowed | Procedure, Template 1 and training record
Note on D1: User name: Questions assessor/auditor will ask

## Asset Management
Domain/Capability | Practice | CMMC Reference | Recommended Actions/Description | Current Company Procedure/Process | Procedure Notes - Who, What When, Where and How | System Security Notes | Form/Meeting Notes | Template 1 | Training | Assessment Artifact(s) [In addition to applicable procedure] | Plan of Action | % Complete
ASSET MANAGEMENT (AM)
Asset management practices ensure that technology assets are identified, inventoried and managed.
No practices at Level 1
|  |  | It is highly recommended that a company keep track of its IT assets - just as it would any other asset. Should have a list of all IT assets to include serial #, who is using the assets, when assets are returned, etc. See Asset Inventory tab. |  |  |  |  | Y

## Audit & Accountability
Domain/Capability | Practice | CMMC Reference | Recommended Actions/Description | Current Company Procedure/Process | Procedure Notes - Who, What When, Where and How | System Security Notes | Form/Meeting Notes | Template | Training | Assessment Artifact(s) | Plan of Action | % Complete
AUDIT AND ACCOUNTABILITY (AU)
Audit and accountabiity is defined as a chronological record that reconstructs and examines the sequence of activites from inception to final result to ensure that the actions can be traced uniquely to that user.
No practices at Level 1

## Awareness & Training
Domain/Capability | Practice | CMMC Reference | Recommended Actions/Description | Current Company Procedure/Process | Procedure Notes - Who, What When, Where and How | System Security Notes | Form/Meeting Notes | Template | Training | Assessment Artifact(s) | Plan of Action | % Complete
AWARENESS & TRAINING (AT)
No practices at Level 1
While there are no Awareness & Training practices in Level 1, it is highly recommended that employees be trained on cybersecurity, how it is implemented in your company and their responsibilities with regard to cybersecurity. Training recommendations are provided on each Domain tab that has CMMC Level 1 Practice requirements. Click on the training tab for additional information.

## Configuration Management
Domain/Capability | Practice | CMMC Reference | Recommended Actions/Description | Current Company Procedure/Process | Procedure Notes - Who, What When, Where and How | System Security Notes | Form/Meeting Notes | Template | Training | Assessment Artifact(s) | Plan of Action | % Complete
CONFIGURATION MANAGEMENT (CM)
Configuration management practices focus on defining the configuration and change management process for systems and system components.
No practices at Level 1

## Incident Response
Domain/Capability | Practice | CMMC Reference | Recommended Actions/Description | Current Company Procedure/Process | Procedure Notes - Who, What When, Where and How | System Security Notes | Form/Meeting Notes | Template | Training | Assessment Artifact(s) | Plan of Action | % Complete
INCIDENT RESPONSE (IR)
A cybersecurity incident is an event that significantly affects or could significantly affet organizational assets and services and requires the organization to respond in some way to prevent or limit adverse impacts.
No practices at Level 1
Incident reporting is not required for CMMC Level 1, however it is a good idea to have a plan in place to report major incidents.
Incident reporting is required for CMMC Level 3 and above. If you experience a cybersecurity incident, contact your contracting officer immediately. Free incident report template - https://www.kieri.com/free-incident-response-templates-scenarios/#section3 (scroll down to #4.)

## Maintenance
Domain/Capability | Practice | CMMC Reference | Recommended Actions/Description | Current Company Procedure/Process | Procedure Notes - Who, What When, Where and How | System Security Notes | Form/Meeting Notes | Template | Training | Assessment Artifact(s) | Plan of Action | % Complete
MAINTENANCE (MA)
Maintenance practices ensure that technology assets that support or process CUI, such as hardware, firmware, applications, scanners, copiers, printers, etc. are maintained properly so the data and systems are protected.
No practices at Level 1
Maintenance is not required for CMMC Level 1; however, it is highly recommended that companies keep their technology assets maintained.

## Media Protection
Domain/Capability | Practice | CMMC Reference | Assessment Guide | Recommended Actions/Description | Current Company Procedure/Process | Procedure Notes - Who, What When, Where and How | System Security Notes | Form/Meeting Notes | Template | Training | Assessment Artifact(s) | Plan of Action | % Complete
MEDIA PROTECTION (MP)
Media Protection activities ensure media used to store or transport data is identified and protected. Includes all media - digital and non-digital.
C023 - Protect and control media | Sanitize or destroy information system media containing FCIbefore disposal or release for reuse. | MP.1.118 | - Is system media containing FCI sanitized or destroyed before disposal? - Is system media containing FCI sanitized before it is released for reuse? | Before throwing media away, make sure it doesn't contain FCI. If it contains FCI, clean/purge before reuse, or shred/destroy it |  | Procedure for determining if media contains FCI and how to remove the data. If media is to be reused, how to determine if FCI has been removed. | Easier to comply if media is treated as an asset and managed - when purchased, who uses it, record of cleaning/purging or destruction (including dates) | Asset management form |  | Train those responsible for handling media - whether for reuse or to be destroyed. Train employees on how to handle media that is no longer needed. | Procedure, signed/dated training record, asset management form
Note on D1: User name: Questions assessor/auditor will ask

## Personnel Security
Domain/Capability | Practice | CMMC Reference | Recommended Actions/Description | Current Company Procedure/Process | Procedure Notes - Who, What When, Where and How | System Security Notes | Form/Meeting Notes | Template | Training | Assessment Artifact(s) | Plan of Action | % Complete
PERSONNEL SECURITY (PS)
No practices at Level 1
While there are no practices at Level 1 for the Personnel Security Policy, it is highly recommended that you document your current personnel security policy or develop one. It should include background checks, drug screenings, reference checks and interviews. It is CRITICAL to the security and profitability of your company to hire only those who have been thoroughly vetted - should be a top priority.

## Physical Protection
Domain/Capability | Practice | CMMC Reference | Assessment Guide | Recommended Actions/Description | Current Company Procedure/Process | Procedure Notes - Who, What When, Where and How | System Security Notes | Form/Meeting Notes | Template | Training | Assessment Artifact(s) | Plan of Action | % Complete
PHYSICAL PROTECTION (PE)
Physical protection practices ensure that physical access to FCI/CUI is strictly controlled, managed, and monitored.
C028 - Limit physical acess | Limit physical access to organizational information systems, equipment, and the respective operating environments to authorized individuals. | PE.1.131 | - Are authorized individuals that are allowed physical access identified? - Is physical access to organizational systems limited to authorized individuals? - Is physical access to equipment limited to authorized individuals? - Is physical access to operating environments limited to authorized individuals? | Visitors must sign in and out and be provided a numbered badge that they wear while they are at your place of business. Employees should have a credential - badge, ID card, etc. Printers/scanners and other equipments should be located in a restricted area. |  | Procedure for authorizing access to company facility to include signing in and out and wearing a numbered badge. (ITAR also requires that visitors state the country they are citizens of, so it's a good idea to have that on the sign-in form as well). Procedure for identifying employees that are authorized to access FCI. Procedure for locating equipment in restricted areas. | Physical assets must be protected since they contain valuable data. It is important to know who is in your company's office/building and when they are there. | Visitor sign-in/sign-out form - date/time/badge number/country of origin/who the visitor is there to see | Visitor sheet | Employees should be trained so they know to check for a badge if someone they are not familiar with is in the office/building | Procedure, Visitor sheet, training record
| Escort visitors and monitor visitor activity | PE.1.132 | - Are visitors escorted? - Is visitor activity monitored? | Visitors must be escorted/monitored at all times |  | Procedure for determining who escorts visitors |  |  |  | Employees should be trained to report visitors if they see they are not escorted by an employee | Procedure, training record
|  |  |  | Limit visitor access to only the areas necessary - possibly different badges with different areas of access. Visitors should be clearly distinguishable from regular personnel. |  | Procedure for knowing which parts of the company the visitor has access to. Procedure for identifying visitors. Procedure for review of visitor logs. |  |  |  | Employees should be trained to determine the lowest level of access that should be allowed | Procedure, training record
| Maintain audit logs of physical access | PE.1.133 |  | Keep sign-in/out logs secure and available for audit |  | Who keeps the logs and where. | For larger companies, all employees should have an access number, card, etc. so their entry and exit can be tracked. For smaller companies, develop a method for making it impossible to access the office/building after normal business hours. |  |  | Person responsible for audit log should be trained on how and where it should be kept | Procedure, training record
| Control and manage physical access devices | PE.1.134 | - Are physical access devices identified? [should be part of asset inventory] - Are physical access devices controlled? - Are physical access devices managed? | Keep logs of who has keys, combinations, entry cards, etc. |  | Procedure for maintaining/reviewing log of physical entry acess devices and for handling missing devices. |  | Asset Inventory Form | Template 1 | Person responsible for asset inventory and/or Template 1 should be trained on how and where it should be kept. Employees should be trained on the procedure for reporting lost/damaged physical access devices. | Procedure, Template 1, Asset inventory
Note on D1: User name: Questions assessor/audit may ask

## Recovery
Domain/Capability | Practice | CMMC Reference | Recommended Actions/Description | Current Company Procedure/Process | Procedure Notes - Who, What When, Where and How | System Security Notes | Form/Meeting Notes | Template | Training | Assessment Artifact(s) | Plan of Action | % Complete
RECOVERY (RE)
Recovery practices are focused on business continuity - sustaining the organization's mission, business function or service.
No practices at Level 1
While there are no Recovery practices for CMMC Level 1, it is highly recommended that companies back up their data on a regular basis, and that back-ups are not stored with servers. At least one copy of the back-up should be stored off-site.

## Risk Mangement
Domain/Capability | Practice | CMMC Reference | Recommended Actions/Description | Current Company Procedure/Process | Procedure Notes - Who, What When, Where and How | System Security Notes | Form/Meeting Notes | Template | Training | Assessment Artifact(s) | Plan of Action | % Complete
RISK MANAGEMENT (RM)
Risk management practices include specific risk mitation practices such as risk identification and planning.
No practices at Level 1 |  |  | See Risk Management tab
Risk Management is not required for CMMC Level 1, however it his highly recommended that companies know the risks and impacts related to every aspect of their business.

## Security Assessment
Domain/Capability | Practice | CMMC Reference | Recommended Actions/Description | Current Company Procedure/Process | Procedure Notes - Who, What When, Where and How | System Security Notes | Form/Meeting Notes | Template | Training | Assessment Artifact(s) | Plan of Action | % Complete
SECURITY ASSESSMENT (CA)
Requires the development of a System Security Plan (SSP). SSPs relate security requirements to a set of security controls and describe at a high level how the security controls meet those security requirements.
No practices at Level 1
CMMC Level 1 has no requirement to develop a System Security Plan; however, it is highly recommended that an SSP be developed. The plan can be tailed to CMMC Level 1 practices.

## Situational Awareness
Domain/Capability | Practice | CMMC Reference | Recommended Actions/Description | Current Company Procedure/Process | Procedure Notes - Who, What When, Where and How | System Security Notes | Form/Meeting Notes | Template | Training | Assessment Artifact(s) | Plan of Action | % Complete
SITUATIONAL AWARENESS (SA)
Situational awareness practices forcus on providing a Common Operating Picture that informs and supports risk-based decision making.
No practices at Level 1 |  |  | Consider subscribing to the U.S. Cybersecurity & Infrastructure Security Agency (CISA) bulletins - https://www.cisa.gov/cybersecurity.
There are no Situational Awareness requirements for CMMC Level 1; however it is highly recommended that companies receive and respond to threat intelligence.

## System & Comms Protection
Domain/Capability | Practice | CMMC Reference | Assessment Guide | Recommended Actions/Description | Current Company Procedure/Process | Procedure Notes - Who, What When, Where and How | System Security Notes | Form/Meeting Notes | Template | Training | Assessment Artifact(s) | Plan of Action | % Complete
SYSTEM & COMMUNICATIONS PROTECTION (SC)
System and Communications Protection activites ensure the organization is actively identifying, managing and controlling all system and communication channels that store or transmit data that must be protected.
C039 - Control communications at system boundaries | Monitor, control, and protect organizational communications (i.e., information transmitted or received by organizational information systems) at the external boundaries and key internal boundaries of the information systems. | SC.1.175 | - Is the external system boundary defined? - Are key internal system boundaries defined? - Are communications monitored at the external system boundary? - Are communications monitored at key internal boundaries? - Are communications controlled at the external system boundary? - Are communications controlled at key internal boundaries? - Are communications protected at the external system boundary? - Are communications protected at key internal boundaries? | Use Web Proxy and/or firewall |  |  | When an employee uses a company computer to go to a website, a web proxy makes the requires on the user's behalf, looks at the web request, and decides if it should the employee go to the website. A firewall controls access from the inside and outside, protecting information and resources stores on the company's network by stopping unwanted traffic on the internet from getting to the company's networks and information systems (websites with certain content are blocked) |  |  | IT trained on the use of web proxies and firewalls | Procedure, training record
| Implement subnetworks for publicly accessible system components that are physically or logically separated from internal networks | SC.1.176 | - Are publicly accessible system components identified? - Are subnetworks for publicly accessible system components physically or logicaly separated from internal networks. | Create demilitarized zone - DMZ - for company websites that contain downloadable company forms - i.e. separate the publicly accessible systems from the internal systems that need to be protected. For example, a downloadable employment application, event invitation, etc. Don't provide guest access to your network - e.g. don't post your wifi password for everyone to use. |  |  | To separate a subnetwork physically, a company can put in boundary control devices such as routers, gateways, and firewalls | Approval form for company website with downloadable forms |  | Employees trained to understand the implications of public accessibility of downloadable documents, and procedure for getting approval. | Procedure, training record, approval form
Note on D1: User name: Questions assessors/auditors may ask

## System & Info. Integrity
Domain/Capability | Domain | Practice | CMMC Reference | Assessment Guide | Recommended Actions/Description | Current Company Procedure/Process | Procedure Notes - Who, What When, Where and How | System Security Notes | Form/Meeting Notes | Template | Training | Assessment Artifact(s) | Plan of Action | % Complete
SYSTEM INFORMATION INTEGRITY (SI) | System & Information Integrity (SI)
System & Information Integrity activities ensure that technology assets such as computers and software that contain FCI/CUI are continuously monitored to detect security violations. Email must be monitored and protect to detect malicious activity.
C040 - Identify and manage information system flaws | C040 - Identify and manage information system flaws | Identify, report, and correct information and information system flaws in a timely manner. | SI.1.210 | - Is the time within which to identify system flaws specified? - Are system flaws identified within the specified time frame? - Is the time within which to report system flaws specified? - Are system flaws reported within the specified time frame? - Is the time within which to correct system flaws specified? - Are system flaws corrected within the specified time frame? | Process to review relevant vendor information updates regarding common problems or weaknesses and execute patch management for software, including the operating system and applications |  | Define time frames within which flaws are identified, reported and corrected. |  |  |  | IT trained on process for keeping up to date on the latest threats and patch management | Procedure, training record
[5 empty] | Purchase maintenance packages from vendors for hardware and operating systems to ensure timely access to updates | [5 empty] | Procurement should be trained to purchase maintenance packages | Procedure, training record
C041 - Identify malicious content | C041 - Identify malicious content | Provide protection from malicious code at appropriate locations within the organizational information systems. | SI.1.211 | - Are designated locations for malicious code protection identified? - Is protection from malicious code provided at designated locations? | Install anti-malware software. |  | Document system components where malicious code protection must be provided. | Malicious code can be viruses, spyware, a trojan horse - typically hidden in emails, email attachments, or while accessing the web. |  |  | Employees should be trained on how to identify malicious code - particulary in emails/attachments | Procedure, training record
|  | Update malicious code protection mechanisms when new releases are available. | SI.1.212 | - Are malicious code protection mechanisms updated when new releases are available? | Configure anti-malware software to automatically update to the latest antivirus code and definitions of all known malware |  | Procedure for updates - how often, who is responsible, etc? |  |  |  | IT trained on importance of updating malicious code protection | Procedure, training record
|  | Perform periodic scans of the information system and real-time scans of files from external sources as files are downloaded, opened or executed | SI.1.213 | - Is the frequency for malicious codes defined? - Are malicious code scans performed within the defined frequency? - Are real-time malicious code scans of files from external sources as files are downloaded, opened or executed performed? | Develop a plan for real-time and periodic scans |  | Procedure for scans - how often, who is responsible? |  | Form for scheduling scans to include the results of the scan |  | IT trained on the importance of real-time and periodic scans | Procedure, training record and scan scheduling form
Note on E1: User name: Questions assessors/auditors may ask